STATEMENT OF WORK NO. 1

AFINITI GROWTH FOUNDATION SPRINT

THIS STATEMENT OF WORK (the “Statement of Work”) by and between Afiniti Inc., (“Company”) and Nick Talbert d/b/a Strategnik (“Service Provider”) is effective as of the last date of signature below, and upon execution will be incorporated into the Master Services Agreement between Company and Service Provider dated [EFFECTIVE DATE OF MASTER SERVICES AGREEMENT] (the “Agreement”).  Capitalized terms used in this Statement of Work will have the same meaning as set forth in the Agreement.

Company hereby engages Service Provider to provide Services, as follows:

- Services.  Service Provider will provide the following Services and Materials to Company:

This Statement of Work covers a 4-week foundation sprint to establish the analytics infrastructure, SEO foundation, content strategy, ABM campaign architecture, and nurture program that Afiniti needs to become visible in both traditional and AI-powered search.

Key principle: Strategnik delivers strategy, frameworks, specifications, campaign architecture, analytics configuration, and step-by-step written setup guides and tutorials for every technology platform Afiniti's team needs to operate. Strategnik does not set up, configure, or deploy ad platforms, email platforms, or CRM/form systems. Afiniti's team executes all platform setup and ongoing implementation — including WordPress publishing, ad platform configuration, MailChimp deployment, Salesforce/form integration, creative production, and target account research — using Strategnik's written guides and specifications. Afiniti owns all platform accounts, media spend, and billing credentials.

# Engagement Overview

| Workstream | Hour Range | Cost Range | Weeks |
| --- | --- | --- | --- |
| SEO + Schema + Analytics Infrastructure | 28–34 hrs | $5,600–$6,800 | 1–2 |
| Content Strategy + Editorial Architecture | 27–34 hrs | $5,400–$6,800 | 1–4 |
| ABM Program + Campaign Architecture | 32–40 hrs | $6,400–$8,000 | 2–4 |
| Nurture Program Design | 12–16 hrs | $2,400–$3,200 | 3–4 |
| Project Management + Onboarding | 17–21 hrs | $3,400–$4,200 | 1–4 |
| TOTAL | 116–141 hrs | $23,200–$28,200 | 4 weeks |

Midpoint estimate: ~128 hours / ~$25,600. Billed against actual hours worked with deliverable log. Target pace: ~30 hours/week, front-loaded.

# Workstream 1: SEO + Schema + Analytics Infrastructure

Estimated hours: 28–34 | Primary weeks: 1–2

Audit existing site pages, deliver SEO restructuring specifications, write production-ready JSON-LD schema markup, and build GA4 + Google Tag Manager from scratch to establish the conversion tracking and audience optimization structure required for ABM and nurture campaigns.

| Strategnik Delivers | Afiniti Executes |
| --- | --- |
| SEO Audit Template (spreadsheet): page-by-page scoring rubric with fields for title tag, meta description, H1/H2 structure, keyword density, internal links, and content gaps — with scoring criteria and a worked example row | Complete one row per site page using the template and scoring rubric |
| SEO Strategic Review (PDF report): prioritized recommendations — page-level title/meta/heading rewrites, keyword targeting changes, internal linking map, and content gap analysis with priority ranking | Implement meta tag, heading, and content updates per the report's page-level specifications |
| JSON-LD Schema Code Files (code per page): production-ready structured data markup for each site page — Organization, FAQPage, Article, BreadcrumbList, and VideoObject types as applicable, validated against Google's Rich Results Test. Accompanied by a Schema Implementation Guide (PDF) | Copy and paste schema code into each page's HTML head or WordPress custom field |
| GA4 Property (live configuration): fully configured Google Analytics 4 property with data streams, events, conversions, audience definitions for remarketing, and cross-domain tracking | — |
| GTM Container (live configuration): Google Tag Manager container with conversion event tags, custom triggers, variables, and audience-building tags — exported as a shareable container JSON. Accompanied by a GTM Installation Guide (PDF) | Install GTM container snippet in site header/footer per provided instructions |
| Conversion Tracking Architecture (PDF diagram): visual map of all tracked events, their triggers, which GA4 goals they feed, and which audiences they build | — |
| SEO Plugin Configuration Spec (PDF): step-by-step Yoast or RankMath settings document with screenshots | Install plugin and configure settings per the spec document |
| AI Crawler Access Audit (PDF checklist): current robots.txt review, recommended directives for OAI-SearchBot, PerplexityBot, ClaudeBot, and Googlebot, plus sitemap submission checklist | Update robots.txt and submit sitemaps per checklist |
| Stale Page Removal Instructions (PDF): list of pages flagged for removal in Google Search Console with rationale and step-by-step removal request process | Submit removal requests in Search Console per instructions |

# Workstream 2: Content Strategy + Editorial Architecture

Estimated hours: 27–34 | Primary weeks: 1–4

Build the complete content architecture for Afiniti's SEO and AEO (AI Engine Optimization) visibility strategy. Deliverables are detailed content briefs, structural frameworks, keyword targeting, editorial standards, and review feedback on Afiniti's drafts. Strategnik does not write finished articles.

| Strategnik Delivers | Afiniti Executes |
| --- | --- |
| Pillar Page Brief (PDF, ~8–10 pages): "What Is Outcome Orchestration?" — complete 3,000+ word outline with section-by-section structure, target keywords, AEO-optimized FAQ pairs, internal linking map, schema specs, and competitive positioning notes | Write the full article following the brief's structure and keyword targets |
| 5 Definitions Hub Page Briefs (PDF, ~3–4 pages each): one brief per page with primary/secondary keyword targets, H1/H2 structure, FAQ pairs for schema, word count target, and internal linking instructions | Write each page from its brief |
| 2 Competitor Comparison Frameworks (PDF + spreadsheet): differentiation matrix mapping Afiniti vs. competitors across features, pricing model, integration depth, and use cases — plus a page-level content brief for each comparison page | Gather competitive data using Strategnik's research template before frameworks are built |
| 4 Blog Article Briefs (PDF, ~2–3 pages each): keyword target, search intent analysis, outline with H2/H3 structure, key points to cover, CTA placement, and word count guidance | Write each article from its brief |
| Case Study Framework + Interview Guide (PDF): reusable case study template structure (Challenge/Solution/Results), VMO2-specific interview question set organized by section, data points to collect, and approval workflow | Coordinate VMO2 interviews, conduct them using the guide, and write the draft |
| AEO Restructuring Template + Worked Example (PDF + marked-up example): before/after restructuring of one existing blog post — plus a blank template checklist for the remaining posts | Apply the template and checklist to restructure 4 remaining existing posts |
| 12-Week Editorial Calendar (spreadsheet): week-by-week publishing schedule with content type, target keyword, assigned owner, draft deadline, publish date, and internal linking dependencies | Follow the calendar for ongoing content production beyond the sprint |
| Editorial Standards Guide (PDF, ~6–8 pages): brand voice definition, formatting rules, heading hierarchy standards, CTA conventions, image/alt-text requirements, AEO structural requirements, and a style checklist | — |
| Editorial Review + Markup (annotated PDFs or Google Doc comments): 2–3 rounds of tracked-changes feedback on Afiniti's content drafts with specific rewrites, structural edits, and SEO/AEO compliance notes | Revise drafts per feedback and resubmit |
| AI Content Production Template (configured Claude Project/Skill, Google Gem, or CustomGPT): custom prompting system pre-loaded with Afiniti's editorial standards, AEO formatting rules, brand voice, schema requirements, and keyword targeting logic | Use the AI template for ongoing content drafting at scale |
| WordPress Publishing Guide (PDF, ~4–6 pages): step-by-step instructions for publishing content to Afiniti's WordPress site following SEO and AEO standards | Follow the publishing guide for all content going live on the site |

# Workstream 3: ABM Program + Campaign Architecture

Estimated hours: 32–40 | Primary weeks: 2–4

Design and deliver a complete ABM program including ICP definition, campaign architecture, use-case-to-segment mapping, contact identification across 500 target accounts, and creative briefs.

| Strategnik Delivers | Afiniti Executes |
| --- | --- |
| ICP + Buying Committee Document (PDF, ~6–8 pages): ideal customer profiles per vertical (telco, financial services, insurance, healthcare, travel) with firmographic criteria, pain points, buying triggers, and a buying committee map | — |
| Target Account Research Template + Scoring Framework (spreadsheet): pre-built columns with a weighted scoring formula — with instructions and 5 example rows completed | Research and populate 500 company rows using the template, scoring criteria, and instructions provided |
| Account Prioritization Report (PDF + annotated spreadsheet): scored and tiered account list (Tier 1/2/3) with rationale for top-priority selections and recommended targeting sequence | — |
| Enriched Contact List (spreadsheet): 2–3 key contacts per priority account across 500 targets — name, title, email, LinkedIn URL, verified via prospecting tools. Accompanied by an Ongoing Enrichment + Agentic Operations Guide (PDF) | Own ongoing data enrichment, list hygiene, and contact maintenance beyond the sprint |
| Use Case-to-Segment Map (PDF diagram + spreadsheet): visual matrix mapping each vertical and persona to specific use cases, messaging angles, content assets, and value propositions | — |
| Campaign Architecture Document (PDF, ~12–15 pages): channel strategy (LinkedIn, Google, Meta, email), sequence logic with timing diagrams, targeting tier definitions, audience build specs per platform, budget allocation framework, and KPI targets per channel. Includes Campaign Launch Checklist. | Build and launch campaigns in ad platforms following the architecture document |
| Creative Briefs (PDF, 3–5 briefs): one per segment/channel combination — ad copy variants, messaging framework, visual direction with reference examples, size/format specs per platform, and A/B testing recommendations | Produce display ads, social ads, and landing pages from the creative briefs |
| Partner Data Integration Strategy (PDF, ~3–4 pages): framework for identifying Five9/NICE/AWS customer overlap as targeting input, recommended data sources, matching methodology | Coordinate with partners to access customer overlap data and co-marketing opportunities |
| ABM Campaign Playbook (PDF, ~20–25 pages): comprehensive reference combining all of the above into a single operational document with campaign launch checklist, ongoing optimization playbook, reporting cadence, and enrichment tool/cadence recommendations | — |
| Ad Platform Setup Guides (3 PDFs, ~5–8 pages each): step-by-step explainer documents for LinkedIn Campaign Manager, Google Ads, and Meta Business Manager — covering account creation, pixel/tag installation, audience building, campaign structure setup, budget allocation, bid strategy, and conversion tracking configuration | Follow setup guides to create and configure ad platform accounts; grant Strategnik viewer/analyst access. Own all media spend and billing credentials. |
| Form + CRM Integration Guide (PDF, ~3–4 pages): recommended form provider options (Pardot, HubSpot Forms, Formstack, or native Web-to-Lead), setup instructions, field mapping to Salesforce, lead routing rules, and testing checklist | Implement form provider and Salesforce integration following the guide; align sales team on follow-up process |

# Workstream 4: Nurture Program Design

Estimated hours: 12–16 | Primary weeks: 3–4

Design the nurture program strategy, write the email sequence copy, and define segmentation logic. All deliverables include operational setup guides so Afiniti's team can build and launch in MailChimp without external support.

| Strategnik Delivers | Afiniti Executes |
| --- | --- |
| Nurture Strategy Document (PDF, ~8–10 pages): visual flow diagram showing entry points, segment paths, branching logic, timing between emails, conversion goals at each stage, and exit/handoff triggers to sales | — |
| Email Sequence Copy (Word/Google Doc): 5–7 complete emails per nurture track with subject lines (primary + A/B variant), preheader text, full body copy, CTAs, and merge field placeholders | Design email templates and produce HTML creative from the copy document |
| Segmentation + Lead Scoring Criteria (PDF + spreadsheet): scoring model with point values per action (page visit, download, email open, form fill), qualification thresholds for MQL/Opportunity handoff, and segment definitions with entry criteria | — |
| MailChimp Setup + Automation Guide (PDF, ~6–8 pages): step-by-step build instructions with annotated screenshots — exact sequence logic, list/audience setup, tag structure, automation workflow configuration, timing delays, conditional splits, merge field mapping, and a testing checklist | Build automation workflows, lists, and segments in MailChimp following the implementation brief. Configure form provider + Salesforce integration for lead capture and routing. Own ongoing nurture monitoring, optimization, lead routing, and sales handoff. |

# Workstream 5: Project Management + Onboarding

Estimated hours: 17–21 | Weeks: 1–4 (ongoing)

| Strategnik Delivers | Afiniti Provides |
| --- | --- |
| Onboarding Audit (PDF, ~4–5 pages): current analytics configuration assessment, tool access inventory with gap list, stakeholder map, and sprint kickoff agenda with role assignments | Provide tool access and admin credentials (GA4, GSC, SEMrush/Ahrefs, WordPress, social accounts) |
| AI Visibility Baseline Report (PDF + spreadsheet): results from 15 high-intent prompts tested across ChatGPT, Perplexity, Claude, Gemini, and Google AI Overviews — documenting where Afiniti is cited and where competitors appear instead | Provide historical analytics data and existing reporting for context |
| Weekly Status Reports (PDF or email): deliverable progress tracker, hours logged against estimate, blockers/dependencies flagged, next-week priorities, and any scope adjustment recommendations | Internal stakeholder availability for onboarding and weekly strategy calls |
| 30-Day AI Visibility Re-Test (PDF + spreadsheet): same 15 prompts re-tested with before/after comparison, citation changes documented, and recommendations for continued optimization | Subject matter expert access for content review and technical validation |
| Month 2–12 Roadmap + KPI Baselines (PDF, ~6–8 pages): phased growth plan with quarterly milestones, channel-specific KPI targets, budget recommendations, headcount/resource needs, and decision criteria for scaling or pivoting each channel | Assign dedicated resource(s) to account research, page audits, and content writing. Ad platform accounts operational (Meta, Google Ads, LinkedIn) with Strategnik access by Week 3. Form capture solution configured and routing to Salesforce before campaign launch. |

# Prerequisites & Dependency Risks

| Prerequisite | Needed By | Risk | Impact If Delayed |
| --- | --- | --- | --- |
| Target account research (Afiniti populates list using Strategnik's criteria and template) | End of Week 2 | MEDIUM | ABM campaign architecture proceeds but targeting cannot be validated against a live account list |
| Page-by-page SEO audit completion (Afiniti fills template) | End of Week 1 | MEDIUM | Strategic SEO recommendations delayed; schema delivery proceeds on available pages only |
| Ad platform accounts created (Meta, Google Ads, LinkedIn) | Week 3 | MEDIUM | Campaign architecture delivered but cannot be validated against live platform configuration |
| Form provider + SFDC integration operational | Week 4 | MEDIUM | Nurture and ABM campaigns ready to launch but no lead capture mechanism in place |
| Competitor research data gathered (Afiniti fills research template) | End of Week 2 | LOW | Comparison page briefs delivered with gaps; Strategnik supplements where possible |
| GTM container snippet installed on site | Week 2 | LOW | GA4/GTM configured but not collecting data until installed |

- Completion.  The Services will be completed within four weeks from project kickoff date as follows:

# Weekly Sprint Timeline

## Week 1: Foundation (Target: ~34 hours)

Strategnik:

- Strategic onboarding: analytics audit, tool access, stakeholder alignment

- AI visibility baseline: 15-prompt battery across ChatGPT, Perplexity, Claude, Gemini, AI Overviews

- GA4 property + GTM container setup from scratch

- Conversion tracking architecture: event tags, triggers, audience definitions

- SEO audit template + rubric delivered to Afiniti's team

- JSON-LD schema templates built; first pages delivered

- Content architecture: pillar page brief, definitions hub mapping, editorial calendar framework

- ICP definition + target account criteria delivered to Afiniti's team

Afiniti's team (in parallel):

- Begin page-by-page SEO audit using template (due end of Week 1)

- Install GTM container snippet on site

- Begin target account research using Strategnik's criteria, template, and scoring framework

- Begin ad platform account creation (Meta, Google Ads, LinkedIn)

## Week 2: SEO Delivery + Content Briefs + ABM Strategy (Target: ~32 hours)

Strategnik:

- Complete JSON-LD schema delivery for all site pages

- Strategic SEO review layered on Afiniti's completed audits

- Pillar page brief delivered: "What Is Outcome Orchestration?"

- 5 definitions hub page briefs delivered

- 12-week editorial calendar delivered

- Editorial standards document delivered

- ABM campaign architecture begins: use-case mapping, channel strategy, targeting tiers

- Competitor research template delivered to Afiniti's team

Afiniti's team (in parallel):

- Continue target account research; deliver completed list by end of Week 2

- Deliver competitor research data using template (due end of Week 2)

- Begin writing pillar page from brief

- Ad platform accounts operational with Strategnik access granted

## Week 3: ABM Build + Remaining Briefs + Nurture (Target: ~32 hours)

Strategnik:

- Target account list review, scoring, and prioritization

- Contact identification + initial enrichment across 500 target accounts using prospecting tools

- ABM campaign playbook + creative briefs delivered

- 2 competitor comparison page frameworks delivered

- 4 blog article briefs delivered

- Case study framework + interview guide delivered

- Nurture program design begins: flow mapping, segmentation logic

- Editorial feedback: first review cycle on Afiniti's drafts

Afiniti's team (in parallel):

- Continue content writing from briefs

- Begin campaign asset production from creative briefs

- Form provider + Salesforce integration setup

## Week 4: Nurture Delivery + Sprint Close (Target: ~24 hours)

Strategnik:

- Nurture program delivered: strategy doc, email copy, segmentation criteria, MailChimp brief

- AEO restructuring template + worked example delivered

- AI content production template delivered: custom Claude Project/Skill, Google Gem, or CustomGPT configured with Afiniti's editorial standards, AEO rules, and brand voice

- Second editorial review cycle on Afiniti's content drafts

- 30-day AI visibility re-test: same 15 prompts, measured change

- Ongoing enrichment recommendations delivered as part of ABM playbook

- Month 2–12 roadmap + KPI baselines delivered

- Sprint retrospective and handoff call

Afiniti's team (in parallel):

- Apply AEO restructuring to 4 existing blog posts using template

- Publish first content pieces

- Campaign deployment preparation in ad platforms

- Form/SFDC integration tested and operational

- MailChimp automation build from implementation brief

# Expected Outcomes & Pipeline Projections

Note: The following projections are provided for planning purposes and are based on standard B2B ABM conversion benchmarks. Service Provider makes no guarantee of specific business outcomes, pipeline volume, or revenue results.

## Conversion Assumptions

| Funnel Stage | Standard Benchmark | Conservative (70%) |
| --- | --- | --- |
| Account → Lead | 15% | 10.5% |
| Lead → MQL | 60% | 60% |
| MQL → Opportunity | 27% | 27% |
| Opportunity → Closed Won | 20% | 20% |
| Average Selling Price | $150K–$250K | $150K–$250K |

## Conservative Scenario: 4-Quarter Aggregate Pipeline

Applies a 70% factor to top-of-funnel lead generation, reflecting Afiniti's current zero brand visibility, absent content engine, and post-bankruptcy perception headwinds. This is the recommended planning scenario for the first 12 months.

| Stage | Q2 2026 | Q3 2026 | Q4 2026 | Q1 2027 | 4Q Total |
| --- | --- | --- | --- | --- | --- |
| New Accounts | 500 | 200 | 300 | 400 | 1,400 |
| Leads | 13 | 25 | 27 | 82 | 147 |
| MQLs | 8 | 15 | 16 | 49 | 88 |
| Opportunities | 2 | 4 | 5 | 13 | 24 |
| Closed Won | 0–1 | 1 | 1 | 2–3 | 4–5 |
| Revenue (at $200K ASP) | $0–$200K | $200K | $200K | $400–$600K | $800K–$1.25M |

## Timeline to Results

Enterprise B2B sales cycles for contact center AI solutions typically run 6–9 months from first touch to closed deal. The 4-week sprint builds the engine. Visible pipeline impact begins in Q2–Q3 2026. Meaningful closed revenue arrives in Q4 2026–Q1 2027. Evaluating this program at 90 days on closed revenue would be premature. The right 90-day metrics are leads generated, MQLs qualified, and opportunities entering pipeline.

- Service Provider Representative. Administration and Payment Contact: Nick Talbert, nick@strategnik.com

- Company Representative. Ayanna Atontsa, Ayanna.Fowlkes@afiniti.com

- Compensation.  The Service Fee due Service Provider for Services under this Statement of Work is $200 per hour, with total Service Fees estimated to be between $23,200 to $28,200 based on 116-141 hours of work. Invoices will reflect the total number of hours worked and deliverables met. All amounts due under this Statement of Work No. 1 will be invoiced in United States Dollars to the attention of Afiniti Accounts Payable Team at afiniti.AP@afiniti.com. Payment will be made in accordance with Section 4 (Fees and Payments) of the Agreement.

All terms and conditions of the Agreement will apply to this Statement of Work.  In the event of any conflict between this Statement of Work and the terms of the Agreement, the terms of the Agreement will control.

# STATEMENT OF WORK NO. 1 AGREED TO AND ACCEPTED BY:

| AFINITI, INC. By: Print Name: Title: Date: | NICK TALBERT D/B/A STRATEGNIK By: Print Name: Title: Date: |
| --- | --- |